## Sheet1
ID | Sprint 0 Task | Owner | Priority | Status | ID | Sprint 1 Task | Owner | Priority | Status
SB-01 | Study Pharmaceutical Business Problem | Thomas, Sanika And Alfred | High | Completed | SB1-01 | Analyze Selected Pharmaceutical Source Systems | Thomas | High | Completed
SB-02 | Identify Business Stakeholders | Thomas | High | Completed | SB1-02 | Prepare Source Inventory | Sanika | High | Completed
SB-03 | Prepare Business Requirements Document (BRD) | Thomas and Sanika | High | Completed | SB1-03 | Prepare Data Dictionary | Thomas | High | Completed
SB-04 | Identify Pharmaceutical Data Sources & Datasets | Thomas, Sanika And Alfred | High | Completed | SB1-04 | Develop CSV Ingestion Pipeline | Sanika | High | Completed
SB-05 | Define Project Scope | Thomas | High | Completed | SB1-05 | Develop Excel Ingestion Pipeline | Thomas | High | Completed
SB-06 | Design High-Level Solution Architecture | Alfred | High | Completed | SB1-06 | Develop JSON Ingestion Pipeline | Sanika | High | Completed
SB-07 | Create Git/GitHub Repository | Sanika | High | Completed | SB1-07 | Develop XML Ingestion Pipeline | Thomas | High | Completed
SB-08 | Create Enterprise Repository Structure | Sanika | High | Completed | SB1-08 | Develop SQL Ingestion Pipeline | Alfred | High | Completed
SB-09 | Prepare Product Backlog | Alfred | High | Completed | SB1-09 | Load Raw Data into PostgreSQL Staging | Thomas | High | Completed
SB-10 | Sprint Backlog | Alfred | High | Completed | SB1-10 | Implement ETL Logging & Exception Handling | Alfred | High | Completed
SB-11 | Prepare Project Charter | Sanika | High | Completed | SB1-11 | Commit ETL Artifacts to Git/GitHub | Alfred | High | Completed